## Sheet1
S.No | Pending Task | Start Date | End Date | Due Date | Remarks
1 | Lookup Creation for request item (LOV) | 2025-08-29 |  | 2025-08-29
2 | Request Page (Dynamic content) validation process | 2025-08-29 |  | 2025-09-02
3 | Master-Detail Page Testing (Insert,Update,Delete) | 2025-09-03 |  | 2025-09-03
4 | Request Page (Dynamic content) Testing (Insert,Update,Delete) | 2025-09-04 |  | 2025-09-04
5 | EBS Workflow Approval Process creation and Implement in Apex | 2025-09-05 |  | Based on workflow design confirmation